## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) & PROGRESS REPORT
State: | Lagos STATE
Reporting period: | FY 2025
SABER Reform Champion and Focal Person: | TOYIN ANJOUS-ADEMUYIWA / MOBOLAJI ONIMOLE
List of contributing entities: | Ministry of Finance; Economic Planning and Budget; State Treasury Office; Debt Management Office; Lands Bureau; Lagos State Internal Revenue Service; Ministry of Justice; Ministry of Commerce, Cooperative, Trade & Investment; Minitstry of Agriculture; Ministry of Transportation; Office of Transformation, Creativity and Innovation (HOS-Office); Ministry of Physical Planning and Urban Development, Ministry of Housing; Office of Public Private Partnership; Public Procurement Agency, Office of Taxation and Revenue
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  | 2024-12-27

## 2025 BERAP
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date
1 | Improved efficiency in property registration and sustainability of the land-based investment process | Enhance the administration and management of land in Lagos State; Improve transparency of property registration | Embark on Post-Digitisation and Indexing of CofOs (registered from 1 January 2012 to December 31, 2024) by Integrating the Digitised CofOs with other State Databases at eGIS and Property Tax (Land Use) | Integrate at least 50% of Digitize and archived CofOs with key State Data Bases i.e, eGIS and Land Use. | Individual and corporate owners of land and property | Lands Bureau | eGIS & Urban Development, Office of the State Surveyor General | REDAN, NIESV | N1,200,000,000.00 | 2025-02-01 | 2025-12-31
|  |  | Update the existing Institutional and Governance Framework to aid the implementation of FRILIA. | - Develop a Statewide Engagement Plan for Stakeholders - Adopt the Outcome in the Land Administration Structure. | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; eGIS and Urban Development; Office of the Surveyor-General. | LCCI, MAN, NASME, NACCIMAREDAN, NIESV | N750,000,000 | 2025-01-01 | 2025-12-31
2 | Improved Regulatory Framework for Private Sector Investment in Fibre Optics Infrastructure | Increase in percentage growth in backbone and middle mile fiber optic deployment investing community. | Increase the deployment of non-GPON fiber (Unified Fibre-Duct) from all operators operating in Lagos State. Ensure the quality of deployment is in line with WBG/ITU-developed Open Standard for terrestrial optical fiber cable data. | Develop Statewide Scalable Deployment Plan. Cover a Minimum of 50% the Central Business Districts with Fibre-Optics Cabling. | Investing Community and Researchers | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N1,000,000,000 | 2025-01-01 | 2025-12-31
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least thrice in 2025 with a view to removing bureaucratic constraints in the business environment in Lagos State | Investors | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N100,000,000.00 | 2025-01-01 | 2025-12-31
3 | Develop an Effective Framework for Public Private Partnership | Establish effective Public-Private Partnership (PPP) framework for the State by developing a Pipeline of Climate Adaptive Projects | Update existing framework to include climate adaptation and mitigation plans in subsequent projects to be delivered using PPP Framework. | Strengthen progressive taxation in Lagos State | Corporate and Retail Investors | OPPP | MEPB, MoJ, MCCTI | LCCI, MAN, NASME, NACCIMA | N50,000,000.00 | 2025-01-01 | 2025-06-30
4 | Improved Investment Promotion Environment | Strengthening the State Capacity to Deepen its Promotion of, and Facilitation of Investments in Lagos State. | Develop tailored measurable strategies that are targeted at specific industries. | Sensitise and Engage MSMEs on Circular Economy Initiatives and Investment Opportunities at least twice in the operational year. Incentivise and monitor the Progress of qualified MSMEs whose business are compliant with globally accceptable principles of Circular Economy | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors. | Ministry of Commerce, Cooperative, Trade and Investments (MCCTI) | MEPB, Office of Revenue and Taxation | LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31
5 | Improve Transparency of Official Fees and Procedures | Increase the Efficiency and Effectiveness of the State's Governance Structure of its Official Fees and Procedures | Digitise existing Grievance Review Mechanism of each of the five State BEE (i.e. Business Enabling Environment -MDAs). Unify all Fees related Activities on a Single Portal to enhance transparency. | Increase in number of business onboarded by the State. Increase in the Internally Generated Revenue of the State due to Voluntary Compoliance and Ease of payment of fees | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Commerce, Cooperative, Trade and Investments | MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
6 | Increased Transpacency of Official Fees and Levies for Interstate Trade and Increased Exporter Certification | Increase transparency in the imposition of fees and levies related to interstate trade | Work with regional States to Standardise Fees Structure Simplify Fees and Levies Computation to engender Voluntary Compliance Consolidate Duplicate Fees and remove outdated fees. Publish the Updated Fees Schedule for the public use. | Increase in Voluntary Compliance, evidenced by increased IGR of not less than 5% in the attributable Revenue Head. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
|  | Improve the certification process for exporters, reducing trade barriers. | Improve Adherence to the 30-Day Timeline for the Execution of Judgement. | Increase in Intra and Inter-Trade Transactions, evidenced by increased Trade Volumes and Registration of New Players in the State Relevant Database. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
7 | Simplified State and Local Business Tax regimes | Simplify Lagos State Tax Systems through Digitisation of the State and Local Tax Administration | Streamline the Certification Process by publishing revised Tax-Codes and reducing the number of documentations required to register and operate. Enhance the Digitisation of Existing Certification Process by expanding the Online Certification Platforms. | Increasing in Compliance and time spent by practionners. Elimination of double taxation and subsequent easing of doing business Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Internal Revenue Service (LIRS) | MoT, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
8 | Quick Determination of Commercial Disputes | Improve Mechanisms for Resolving Commercial Dispute Faster | Increase in the Judicial Capacity of the State by appointing more Magistrates for the growing number of Small Claim Courts. Implementation of Efficiant Case Management by including enhancing Electronic Filing of Cases and Digiting the Status Tracking Process. | Improvement of Service of Summons to not more than 7 Days post successful filing of cases. Delivery of final judgement within 2 weeks of closure of hearing. Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Justice/Judiciary | MoT, MCCTI, MEPB, Office of Revenue and Taxation, LIRS | NBA, LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31
N4,400,000,000
3

## 2025 BERAP PR
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Explanation of Action Not Completed | Next Steps
1 | Improved efficiency in property registration and sustainability of the land-based investment process | Enhance the administration and management of land in Lagos State; Improve transparency of property registration | Embark on Post-Digitisation and Indexing of CofOs (registered from 1 January 2012 to December 31, 2024) by Integrating the Digitised CofOs with other State Databases at eGIS and Property Tax (Land Use) | Integrate at least 50% of Digitize and archived CofOs with key State Data Bases i.e, eGIS and Land Use. | Individual and corporate owners of land and property | Lands Bureau | eGIS & Urban Development, Office of the State Surveyor General | REDAN, NIESV | N1,200,000,000.00 | 2025-02-01 | 2025-12-31 | Delayed | The post-digitisation and integration of Certificates of Occupancy (CofOs) with State databases could not be completed within the 2025 timeline. This was due to ongoing upgrades of the digital archiving system to meet projected international standards upon full integration. | 1. Complete the migration of the Certificate of Occupancy (CofO) Archive Administration Portal to the Lagos State Government, ensuring full ownership, control, and administration of the platform by the State Government (Q3 2026). 2. Reformat archived CofO records to meet international digital archiving standards (Q3–Q4 2026). 3. Finalize the upgrade of the CofO digital archiving system and integrate digitised CofOs with the eGIS and Property Tax/Land Use Charge platforms (Q4 2026).
|  |  | Update the existing Institutional and Governance Framework to aid the implementation of FRILIA. | - Develop a Statewide Engagement Plan for Stakeholders - Adopt the Outcome in the Land Administration Structure. | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; eGIS and Urban Development; Office of the Surveyor-General. | LCCI, MAN, NASME, NACCIMAREDAN, NIESV | N750,000,000 | 2025-01-01 | 2025-12-31 | completed |  | 1. Sustain implementation of the Stakeholder Engagement Plan. 2. Monitor compliance throughout project implementation (Continuous).
2 | Improved Regulatory Framework for Private Sector Investment in Fibre Optics Infrastructure | Increase in percentage growth in backbone and middle mile fiber optic deployment investing community. | Increase the deployment of non-GPON fiber (Unified Fibre-Duct) from all operators operating in Lagos State. Ensure the quality of deployment is in line with WBG/ITU-developed Open Standard for terrestrial optical fiber cable data. | Develop Statewide Scalable Deployment Plan. Cover a Minimum of 50% the Central Business Districts with Fibre-Optics Cabling. | Investing Community and Researchers | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N1,000,000,000 | 2025-01-01 | 2025-12-31 | Completed |  | 1. Expand the Network to cover additional 15% of the Central Business Districts with Fibre-Optics Cabling. This shall bring the total coverage to 65%. Continue network expansion and routine maintenance to sustain service delivery is a continuous programme. (Continuous).
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least thrice in 2025 with a view to removing bureaucratic constraints in the business environment in Lagos State | Investors | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N100,000,000.00 | 2025-01-01 | 2025-12-31 | Completed |  | Continue quarterly stakeholder engagements and monitor implementation outcomes (Quarterly).
3 | Develop an Effective Framework for Public Private Partnership | Establish effective Public-Private Partnership (PPP) framework for the State by developing a Pipeline of Climate Adaptive Projects | Update existing framework to include climate adaptation and mitigation plans in subsequent projects to be delivered using PPP Framework. | Strengthen progressive taxation in Lagos State | Corporate and Retail Investors | OPPP | MEPB, MoJ, MCCTI | LCCI, MAN, NASME, NACCIMA | N50,000,000.00 | 2025-01-01 | 2025-06-30 | Delayed | Integration of climate-adaptive requirements into the PPP framework was not completed within 2025 due to ongoing policy review, stakeholder consultations and approval processes. | 1. Finalise the revised PPP framework (Q4 2026). 2 Obtain Executive approval (Q4 2026). 3. Roll out the revised framework to stakeholders (Q4 2026).
4 | Improved Investment Promotion Environment | Strengthening the State Capacity to Deepen its Promotion of, and Facilitation of Investments in Lagos State. | Develop tailored measurable strategies that are targeted at specific industries. | Sensitise and Engage MSMEs on Circular Economy Initiatives and Investment Opportunities at least twice in the operational year. Incentivise and monitor the Progress of qualified MSMEs whose business are compliant with globally accceptable principles of Circular Economy | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors. | Ministry of Commerce, Cooperative, Trade and Investments (MCCTI) | MEPB, Office of Revenue and Taxation | LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | The activity was not completed within the 2025 implementation timeline because additional internal stakeholder consultations and assessment of participating MSMEs were required before final validation and reporting. | 1. Complete remaining stakeholder engagements (Q3 2026). 2. Finalise MSME assessment and validation (Q3 2026). 3. Publish implementation report (Q4 2026).
5 | Improve Transparency of Official Fees and Procedures | Increase the Efficiency and Effectiveness of the State's Governance Structure of its Official Fees and Procedures | Digitise existing Grievance Review Mechanism of each of the five State BEE (i.e. Business Enabling Environment -MDAs). Unify all Fees related Activities on a Single Portal to enhance transparency. | Increase in number of business onboarded by the State. Increase in the Internally Generated Revenue of the State due to Voluntary Compoliance and Ease of payment of fees | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Commerce, Cooperative, Trade and Investments | MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | Full implementation of the digital platform and grievance review mechanism was delayed due to additional system integration and testing requirements beyond the 2025 implementation period. | 1. Complete system integration and testing (Q3 2026). 2. Deploy the digital platform across relevant MDAs (Q3 2026). 3. Monitor platform performance and user adoption (Q4 2026).
6 | Increased Transpacency of Official Fees and Levies for Interstate Trade and Increased Exporter Certification | Increase transparency in the imposition of fees and levies related to interstate trade | Work with regional States to Standardise Fees Structure Simplify Fees and Levies Computation to engender Voluntary Compliance Consolidate Duplicate Fees and remove outdated fees. Publish the Updated Fees Schedule for the public use. | Increase in Voluntary Compliance, evidenced by increased IGR of not less than 5% in the attributable Revenue Head. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | Review and harmonisation of fees and levies have been substantially completed, with the updated fee structure largely finalized and stakeholder engagement ongoing. | 1. Obtain approval of the revised fee schedule (Q3 2026). 2. Publish the approved fees and levies (Q3 2026). 3. Monitor compliance and implementation (Q4 2026).
|  | Improve the certification process for exporters, reducing trade barriers. | Improve Adherence to the 30-Day Timeline for the Execution of Judgement. | Increase in Intra and Inter-Trade Transactions, evidenced by increased Trade Volumes and Registration of New Players in the State Relevant Database. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | Improvements to the exporter certification process were not completed within the 2025 timeline due to continued inter-agency consultation and finalisation of revised operational procedures. | 1. Finalise harmonised certification procedures (Q3 2026). 2. Roll out the improved certification process (Q3 2026). 3. Monitor certification turnaround time and performance (Q4 2026).
7 | Simplified State and Local Business Tax regimes | Simplify Lagos State Tax Systems through Digitisation of the State and Local Tax Administration | Streamline the Certification Process by publishing revised Tax-Codes and reducing the number of documentations required to register and operate. Enhance the Digitisation of Existing Certification Process by expanding the Online Certification Platforms. | Increasing in Compliance and time spent by practionners. Elimination of double taxation and subsequent easing of doing business Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Internal Revenue Service (LIRS) | MoT, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Completed |  | 1. Sustain monitoring and compliance of the simplificed process. 2. Continuous improvement in digital services delivery; and 3. Periodically review tax administration processes (Continuous).
8 | Quick Determination of Commercial Disputes | Improve Mechanisms for Resolving Commercial Dispute Faster | Increase in the Judicial Capacity of the State by appointing more Magistrates for the growing number of Small Claim Courts. Implementation of Efficiant Case Management by including enhancing Electronic Filing of Cases and Digiting the Status Tracking Process. | Improvement of Service of Summons to not more than 7 Days post successful filing of cases. Delivery of final judgement within 2 weeks of closure of hearing. Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Justice/Judiciary | MoT, MCCTI, MEPB, Office of Revenue and Taxation, LIRS | NBA, LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31 | Completed |  | 1. Continue monitoring the effectiveness of the reforms, 2. strengthen institutional capacity, and 3. undertake periodic reviews to sustain improvements in case management and service delivery (Continuous).
N4,400,000,000

## Lands Bureau (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
1 | Improved efficiency in property registration and sustainability of the land-based investment process | Enhance the administration and management of land in Lagos State; Improve transparency of property registration | Embark on Post-Digitisation and Indexing of CofOs (registered from 1 January 2012 to December 31, 2024) by Integrating the Digitised CofOs with other State Databases at eGIS and Property Tax (Land Use) | Integrate at least 50% of Digitize and archived CofOs with key State Data Bases i.e, eGIS and Land Use. | Individual and corporate owners of land and property | Lands Bureau | eGIS & Urban Development, Office of the State Surveyor General | REDAN, NIESV | N1,200,000,000.00 | 2025-02-01 | 2025-12-31 | ongoing - on time, | The CofO digital archiving system is undergoing upgrade to meet international best practices and standard as requested by SABER | Finalize the upgrade of CofO dgital archiving system and integrate digitised CofOs with other State databases at eGIS and Property Tax/Land Use Charge platforms.

## MoA (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
|  |  | Update the existing Institutional and Governance Framework to aid the implementation of FRILIA. | - Develop a Statewide Engagement Plan for Stakeholders - Adopt the Outcome in the Land Administration Structure. | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; eGIS and Urban Development; Office of the Surveyor-General. | LCCI, MAN, NASME, NACCIMAREDAN, NIESV | N750,000,000 | 2025-01-01 | 2025-12-31 | completed | Lagos State FRILIA Stakeholders Engagment Plan was developed and adopted to enhance land intensive Agriculture investments. | Update and operationalise the existing institutional and governance framework to aid the implementation of FRILIA across land-related investment projects.

## IBILE (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
2 | Improved Regulatory Framework for Private Sector Investment in Fibre Optics Infrastructure | Increase in percentage growth in backbone and middle mile fiber optic deployment investing community. | Increase the deployment of non-GPON fiber (Unified Fibre-Duct) from all operators operating in Lagos State. Ensure the quality of deployment is in line with WBG/ITU-developed Open Standard for terrestrial optical fiber cable data. | Develop Statewide Scalable Deployment Plan. Cover a Minimum of 50% the Central Business Districts with Fibre-Optics Cabling. | Investing Community and Researchers | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N1,000,000,000 | 2025-01-01 | 2025-12-31 | Completed | Deployment of non-GPON fiber (Unified Fibre-Duct) have been expanded by 60% in Central Business Districts for wider coverage in Lagos State. | Ensure that deployment quality aligns with WBG/ITU-developed open standards for terrestrial optical fibre cable data.
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least thrice in 2025 with a view to removing bureaucratic constraints in the business environment in Lagos State | Investors | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N100,000,000.00 | 2025-01-01 | 2025-12-31 | Completed | ISP Stakeholders meetings were held quarterly to upscale Fiber Optic service delivery in Lagos State | Organise periodic information and investor-engagement sessions annually for fibre infrastructure stakeholders

## PPP (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
3 | Develop an Effective Framework for Public Private Partnership | Establish effective Public-Private Partnership (PPP) framework for the State by developing a Pipeline of Climate Adaptive Projects | Update existing framework to include climate adaptation and mitigation plans in subsequent projects to be delivered using PPP Framework. | Strengthen progressive taxation in Lagos State | Corporate and Retail Investors | OPPP | MEPB, MoJ, MCCTI | LCCI, MAN, NASME, NACCIMA | N50,000,000.00 | 2025-01-01 | 2025-06-30 | Ongoing - delayed | Climate Adaptive Projects is being incorporated into the PPP Framework and under review by Ministry of Justice | Finalise Update of the PPP framework to include climate adaptation, mitigation and resilience considerations in subsequent projects delivered through PPP arrangements.

## MCCTI (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
4 | Improved Investment Promotion Environment | Strengthening the State Capacity to Deepen its Promotion of, and Facilitation of Investments in Lagos State. | Develop tailored measurable strategies that are targeted at specific industries. | Sensitise and Engage MSMEs on Circular Economy Initiatives and Investment Opportunities at least twice in the operational year. Incentivise and monitor the Progress of qualified MSMEs whose business are compliant with globally accceptable principles of Circular Economy | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors. | Ministry of Commerce, Cooperative, Trade and Investments (MCCTI) | MEPB, Office of Revenue and Taxation | LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | Key sensitisation activities have been conducted, and stakeholder engagement has progressed well. Assessment and monitoring of participating MSMEs are ongoing, with most targets substantially achieved. | Complete the remaining stakeholder engagements, finalize MSME assessments, and document the overall outcomes and lessons learned.
5 | Improve Transparency of Official Fees and Procedures | Increase the Efficiency and Effectiveness of the State's Governance Structure of its Official Fees and Procedures | Digitise existing Grievance Review Mechanism of each of the five State BEE (i.e. Business Enabling Environment -MDAs). Unify all Fees related Activities on a Single Portal to enhance transparency. | Increase in number of business onboarded by the State. Increase in the Internally Generated Revenue of the State due to Voluntary Compoliance and Ease of payment of fees | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Commerce, Cooperative, Trade and Investments | MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | Most digitisation activities have been completed, and integration of grievance review mechanisms is progressing as planned. The unified fees platform has been substantially developed, with final enhancements underway. | Complete system integration, conduct user testing, onboard remaining MDAs, and commence full implementation.

## MoT (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
6 | Increased Transpacency of Official Fees and Levies for Interstate Trade and Increased Exporter Certification | Increase transparency in the imposition of fees and levies related to interstate trade | Work with regional States to Standardise Fees Structure Simplify Fees and Levies Computation to engender Voluntary Compliance Consolidate Duplicate Fees and remove outdated fees. Publish the Updated Fees Schedule for the public use. | Increase in Voluntary Compliance, evidenced by increased IGR of not less than 5% in the attributable Revenue Head. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | Review and harmonisation of fees and levies have been substantially completed, with the updated fee structure largely finalized and stakeholder engagement ongoing. | • Obtain approval of the revised fee schedule (Q3 2026). • Publish the approved fees and levies (Q3 2026). • Monitor compliance and implementation (Q4 2026).
|  | Improve the certification process for exporters, reducing trade barriers. | Improve Adherence to the 30-Day Timeline for the Execution of Judgement. | Increase in Intra and Inter-Trade Transactions, evidenced by increased Trade Volumes and Registration of New Players in the State Relevant Database. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Delayed | Improvements to the exporter certification process were not completed within the 2025 timeline due to continued inter-agency coordination and finalisation of revised operational procedures. | • Finalise harmonised certification procedures (Q3 2026). • Roll out the improved certification process (Q3 2026). • Monitor certification turnaround time and performance (Q4 2026).

## LIRS (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
7 | Simplified State and Local Business Tax regimes | Simplify Lagos State Tax Systems through Digitisation of the State and Local Tax Administration | Streamline the Certification Process by publishing revised Tax-Codes and reducing the number of documentations required to register and operate. Enhance the Digitisation of Existing Certification Process by expanding the Online Certification Platforms. | Increasing in Compliance and time spent by practionners. Elimination of double taxation and subsequent easing of doing business Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Internal Revenue Service (LIRS) | MoT, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31 | Completed | The review of tax administration processes, digital improvements and taxpayer service initiatives was successfully completed within the 2025 implementation period. | Continue monitoring compliance, enhance digital services and periodically review tax administration processes (Continuous).

## Judiciary (hidden)
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT OF LAGOS STATE FOR YEAR 2025
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
8 | Quick Determination of Commercial Disputes | Improve Mechanisms for Resolving Commercial Dispute Faster | Increase in the Judicial Capacity of the State by appointing more Magistrates for the growing number of Small Claim Courts. Implementation of Efficiant Case Management by including enhancing Electronic Filing of Cases and Digiting the Status Tracking Process. | Improvement of Service of Summons to not more than 7 Days post successful filing of cases. Delivery of final judgement within 2 weeks of closure of hearing. Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Judiciary | MoT, MCCTI, MEPB, Office of Revenue and Taxation, LIRS | NBA, LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31 | Ongoing – On Time | The judicial reform activity was successfully completed within the 2025 implementation timeline through the enhancement of judicial capacity and the implementation of improved case management processes, including digitalisation initiatives aimed at improving efficiency and access to justice. | Continue monitoring the effectiveness of the reforms, strengthen institutional capacity, and undertake periodic reviews to sustain improvements in case management and service delivery (Continuous).