## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) & PROGRESS REPORT
State: | Lagos STATE
Reporting period: | FY 2025
SABER Reform Champion and Focal Person: | TOYIN ANJOUS-ADEMUYIWA / MOBOLAJI ONIMOLE
List of contributing entities: | Ministry of Finance; Economic Planning and Budget; State Treasury Office; Debt Management Office; Lands Bureau; Lagos State Internal Revenue Service; Ministry of Justice; Ministry of Commerce, Cooperative, Trade & Investment; Minitstry of Agriculture; Ministry of Transportation; Office of Transformation, Creativity and Innovation (HOS-Office); Ministry of Physical Planning and Urban Development, Ministry of Housing; Office of Public Private Partnership; Public Procurement Agency, Office of Taxation and Revenue
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  | 2024-12-27

## 2025 BERAP
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) OF LAGOS STATE FOR YEAR 2025
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date
1 | Improved efficiency in property registration and sustainability of the land-based investment process | Enhance the administration and management of land in Lagos State; Improve transparency of property registration | Embark on Post-Digitisation and Indexing of CofOs (registered from 1 January 2012 to December 31, 2024) by Integrating the Digitised CofOs with other State Databases at eGIS and Property Tax (Land Use) | Integrate at least 50% of Digitize and archived CofOs with key State Data Bases i.e, eGIS and Land Use. | Individual and corporate owners of land and property | Lands Bureau | eGIS & Urban Development, Office of the State Surveyor General | REDAN, NIESV | N1,200,000,000.00 | 2025-02-01 | 2025-12-31
|  |  | Update the existing Institutional and Governance Framework to aid the implementation of FRILIA. | - Develop a Statewide Engagement Plan for Stakeholders - Adopt the Outcome in the Land Administration Structure. | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; eGIS and Urban Development; Office of the Surveyor-General. | LCCI, MAN, NASME, NACCIMAREDAN, NIESV | N750,000,000 | 2025-01-01 | 2025-12-31
2 | Improved Regulatory Framework for Private Sector Investment in Fibre Optics Infrastructure | Increase in percentage growth in backbone and middle mile fiber optic deployment investing community. | Increase the deployment of non-GPON fiber (Unified Fibre-Duct) from all operators operating in Lagos State. Ensure the quality of deployment is in line with WBG/ITU-developed Open Standard for terrestrial optical fiber cable data. | Develop Statewide Scalable Deployment Plan. Cover a Minimum of 50% the Central Business Districts with Fibre-Optics Cabling. | Investing Community and Researchers | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N1,000,000,000 | 2025-01-01 | 2025-12-31
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least thrice in 2025 with a view to removing bureaucratic constraints in the business environment in Lagos State | Investors | IBILE Broadband, | Ministry of Innovation science and Technology; LASIMRA and Ministry of Physical Planning | LCCI, MAN, NASME, NACCIMA | N100,000,000.00 | 2025-01-01 | 2025-12-31
3 | Develop an Effective Framework for Public Private Partnership | Establish effective Public-Private Partnership (PPP) framework for the State by developing a Pipeline of Climate Adaptive Projects | Update existing framework to include climate adaptation and mitigation plans in subsequent projects to be delivered using PPP Framework. | Strengthen progressive taxation in Lagos State | Corporate and Retail Investors | OPPP | MEPB, MoJ, MCCTI | LCCI, MAN, NASME, NACCIMA | N50,000,000.00 | 2025-01-01 | 2025-06-30
4 | Improved Investment Promotion Environment | Strengthening the State Capacity to Deepen its Promotion of, and Facilitation of Investments in Lagos State. | Develop tailored measurable strategies that are targeted at specific industries. | Sensitise and Engage MSMEs on Circular Economy Initiatives and Investment Opportunities at least twice in the operational year. Incentivise and monitor the Progress of qualified MSMEs whose business are compliant with globally accceptable principles of Circular Economy | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors. | Ministry of Commerce, Cooperative, Trade and Investments (MCCTI) | MEPB, Office of Revenue and Taxation | LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31
5 | Improve Transparency of Official Fees and Procedures | Increase the Efficiency and Effectiveness of the State's Governance Structure of its Official Fees and Procedures | Digitise existing Grievance Review Mechanism of each of the five State BEE (i.e. Business Enabling Environment -MDAs). Unify all Fees related Activities on a Single Portal to enhance transparency. | Increase in number of business onboarded by the State. Increase in the Internally Generated Revenue of the State due to Voluntary Compoliance and Ease of payment of fees | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Commerce, Cooperative, Trade and Investments | MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
6 | Increased Transpacency of Official Fees and Levies for Interstate Trade and Increased Exporter Certification | Increase transparency in the imposition of fees and levies related to interstate trade | Work with regional States to Standardise Fees Structure Simplify Fees and Levies Computation to engender Voluntary Compliance Consolidate Duplicate Fees and remove outdated fees. Publish the Updated Fees Schedule for the public use. | Increase in Voluntary Compliance, evidenced by increased IGR of not less than 5% in the attributable Revenue Head. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
|  | Improve the certification process for exporters, reducing trade barriers. | Improve Adherence to the 30-Day Timeline for the Execution of Judgement. | Increase in Intra and Inter-Trade Transactions, evidenced by increased Trade Volumes and Registration of New Players in the State Relevant Database. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Transport | MCCTI, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
7 | Simplified State and Local Business Tax regimes | Simplify Lagos State Tax Systems through Digitisation of the State and Local Tax Administration | Streamline the Certification Process by publishing revised Tax-Codes and reducing the number of documentations required to register and operate. Enhance the Digitisation of Existing Certification Process by expanding the Online Certification Platforms. | Increasing in Compliance and time spent by practionners. Elimination of double taxation and subsequent easing of doing business Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Internal Revenue Service (LIRS) | MoT, MEPB, Office of Revenue and Taxation | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2025-01-01 | 2025-12-31
8 | Quick Determination of Commercial Disputes | Improve Mechanisms for Resolving Commercial Dispute Faster | Increase in the Judicial Capacity of the State by appointing more Magistrates for the growing number of Small Claim Courts. Implementation of Efficiant Case Management by including enhancing Electronic Filing of Cases and Digiting the Status Tracking Process. | Improvement of Service of Summons to not more than 7 Days post successful filing of cases. Delivery of final judgement within 2 weeks of closure of hearing. Increase in number of Clearance of Disputes Reported for resolutions (not less than 75%). | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Ministry of Justice/Judiciary | MoT, MCCTI, MEPB, Office of Revenue and Taxation, LIRS | NBA, LCCI, MAN, NASME, NACCIMA | N250,000,000.00 | 2025-01-01 | 2025-12-31
N4,400,000,000
3