## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) & PROGRESS REPORT
State: | Lagos STATE
Reporting period: |  | FY 2023
SABER Focal PersonS: |  | TOYIN ANJOUS-ADEMUYIWA / MOBOLAJI ONIMOLE
List of contributing entities: |  |  | Ministry of Finance; Economic Planning and Budget; State Treasury Office; Debt Management Office; Lands Bureau; Lagos State Internal Revenue Service; Ministry of Justice; Ministry of Commerce, Cooperative, Trade & Investment; Minitstry of Agriculture; Ministry of Transportation; Office of Transformation, Creativity and Innovation (HOS-Office); Ministry of Physical Planning and Urban Development, Ministry of Housing; Office of Public Private Partnership; Public Procurement Agency, Office of Taxation and Revenue
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  |  | 2023-12-29

## BERAP
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) OF LAGOS STATE FOR YEAR 2024
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date
1 | Improved transparency in Land Administration and Land-based Investment Process | (i) Enhance the administration and management of land in Lagos State; (ii)Improve transparency of property registration | Digitize and index CofOs registered from 1 January 2012 to December 31, 2024 | Digitize and archive 75% of CofO | Individual and corporate owners of land and property | Lands Bureau, | Lands Bureau, Ministry of Housing, Ministry of Physical Planning and Urban Development, Office of the State Surveyor General | LCCI, MAN, NASME, NACCIMA | N1,000,000,000.00 | 2024-01-01 | 31-12-24
|  |  | Issue Executive Order on FRILIA | The Executive Order provides a legal basis for the insitution of FRILIA practices in Lagos State | Investors, farmers and land owners | Ministry of Justice | Lands Bureau, Ministry of Housing, Ministry of Physical Planning and Urban Development, Office of the State Surveyor General | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 2024-01-10
|  |  | Institute the Framework for Responsible and Inclusive Land Intensive Agriculture (FRILIA) | (i) Establish a Steering Committee on FRILIA (ii) Create an interministeral consultative platform for FRILIA challenges | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; Ministry of Physical Planning and Urban Development; Ministry of Justice, Ministry of Finance, Ministry of Commerce, Cooperatives, Trade and Investment, LIRS, Office of the Surveyor-General | LCCI, MAN, NASME, NACCIMA | N500,000,000 | 2024-01-01 | 31-12-24
|  |  | Develop FRILIA toolkit | Establish specific tools for implementing FRILIA in the State | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; Ministry of Physical Planning and Urban Development; Ministry of Justice, Ministry of Finance, Ministry of Commerce, Cooperatives, Trade and Investment, LIRS, Office of the Surveyor-General | LCCI, MAN, NASME, NACCIMA | N600,000,000 | 2024-01-01 | 31-12-24
2 | Develop an effective framework for Public Private Partnerships and Improved Investment Promotion Environment | Establish effective Public-Private Partnership (PPP) framework for the State | Create PPP disclosure portal of the pipeline projects | Create a PPP disclosure portal on her website and state official website. | Investors | Office of Public Private Partnership | Ministry of Commerce, Cooperatives, Trade and Investment; Ministry of Economic Planning and Budget; Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | N10,000,000 | 2024-01-01 | 31-03-24
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least twice in 2024 with a view to removing bureaucratic constraints in the business environment in Lagos State | Investors | Office of Public Private Partnership | Ministry of Commerce, Cooperatives, Trade and Investment; Ministry of Economic Planning and Budget; Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | N7,000,000.00 | 2024-01-01 | 31-12-24
|  |  | Develop a PPP Fiscal Commitment and Contingent Liability (FCCL) Management Framework; and (ii) the PPP legal and institutional framework, including guidelines and manual; and (iii) the PPP disclosure framework; | Lagos Global to create a PPP disclosure portal on her website and state official website. | Investors | Office of Public Private Partnership | Ministry of Commerce, Cooperatives, Trade and Investment; Ministry of Economic Planning and Budget; Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | N10,000,000 | 2024-01-01 | 31-03-24
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least twice in 2024 with a view to removing bureaucratic constraints in the business environment in Lagos State | Investors | Office of Public Private Partnership | Ministry of Commerce, Cooperatives, Trade and Investment; Ministry of Economic Planning and Budget; Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | N7,000,000.00 | 2024-01-01 | 31-12-24
|  |  | Establish State Project Facilitation Fund with a minimum funding of 3% of the total pipeline estimated capital investment | Catalyze public private investments with facilitation fund | Investors | Ministry of Finance, Ministry of Budget and Economic Planning | Ministry of Commerce, Cooperatives, Trade and Investment, Office of Public Private Partnership, Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 30-06-24
5 | Simplification of State and Local Business Tax Regimes | This reform is aimed at introducing a fairer and more equitable in Lagos State | At least 10% increase in the number of firms in the state that obtained export certificates from NEPC from the baseline year (2021). | Create incentives for MSMEs engaging in non-oil export | Micro, Small and Medium Entreprises (MSMEs) and investors | LIRS | Ministry of Finance, Office of Taxation and Revenue, Ministry of Economic Planning and Budget, Ministry of Commerce, Cooperatives, Trade and Investment, Ministry of Transportation | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 2024-08-30
|  |  | Amend existing legislation to adopt presumptive turnover tax regime for small businesses | Strengthen progressive taxation in Lagos State | Micro, Small and Medium Entreprises (MSMEs) and investors | LIRS | Ministry of Finance, Office of Taxation and Revenue, Ministry of Economic Planning and Budget, Ministry of Commerce, Cooperatives, Trade and Investment | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 2024-08-30
7 | Quick determination of commercial disputes | This reform area will improve the State Judiciary and strengthen access to an efficient commercial justice system | Develop State Judiciary website | to ensure transparency, the State Judiciary shall establish a functional website | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Judiciary | Ministry of Justice | NBA, LCCI, MAN, NASME, NACCIMA | N20,000,000.00 | 2024-01-01 | 30-06-24
|  |  | Public practice direction on state website | to ensure transparency, the State Judiciary shall establish a functional website | MSMEs | Lagos State Judiciary | Ministry of Justice | NBA, LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 31-12-24
|  |  | Write monthly report for small claims courts from inception of the courts to December 2023 | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis | MSMEs | Lagos State Judiciary | Ministry of Justice | NBA, LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 31-12-24
|  |  | Publish on the State Judiciary website reports for small claims courts on monthly basis | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis | MSMEs | Lagos State Judiciary | Ministry of Justice | NBA, LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 31-12-24
|  |  | Submit dispostion time report to include cases disposed within 60 days | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis and ensuee at least 80% performance achievement | MSMEs | Lagos State Judiciary | Ministry of Justice | NBA, LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 31-12-24
|  |  | Submit execution time report to include judgement executed within 30 days | The Judiciary shall provide a monthly report on the activities of the small claims court on a monthly basis and ensuee at least 80% performance achievement | MSMEs | Lagos State Judiciary | Ministry of Justice | NBA, LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 31-12-24