## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) & PROGRESS REPORT
State: | Lagos STATE
Reporting period: |  | FY 2024
SABER Focal PersonS: |  | TOYIN ANJOUS-ADEMUYIWA / MOBOLAJI ONIMOLE
List of contributing entities: |  |  | Ministry of Finance; Economic Planning and Budget; State Treasury Office; Debt Management Office; Lands Bureau; Lagos State Internal Revenue Service; Ministry of Justice; Ministry of Commerce, Cooperative, Trade & Investment; Minitstry of Agriculture; Ministry of Transportation; Office of Transformation, Creativity and Innovation (HOS-Office); Ministry of Physical Planning and Urban Development, Ministry of Housing; Office of Public Private Partnership; Public Procurement Agency, Office of Taxation and Revenue
URL Link to the published BERAP | https://lagosmepb.org/ease-of-doing-business/
Is this plan approved by the State Executive Council (SEC) |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  |  | 2025-07-31

## FY_2024_BERAP_PR
BUSINESS ENABLING REFORM ACTION PLAN (BERAP) OF LAGOS STATE FOR YEAR 2024 | [11 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Beneficiaries | Responsible MDA | Contributing MDAs | Private Sector Contributors | Estimated costs | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
1 | Improved transparency in Land Administration and Land-based Investment Process | (i) Enhance the administration and management of land in Lagos State; (ii)Improve transparency of property registration | Digitize and index CofOs registered from 1 January 2012 to December 31, 2024 | Digitize and archive 75% of CofO | Individual and corporate owners of land and property | Lands Bureau, | Lands Bureau, Office of e-GIS and Urban Development, Ministry of Housing, Ministry of Physical Planning, Office of the State Surveyor General | LCCI, MAN, NASME, NACCIMA | N1,000,000,000.00 | 2024-01-01 | 31-12-24 | Done 1. The State Government has been able to deepen its Transparent Business process on an Automated End-to-End Workflow platform. 2. The is a sense of complete paradigm shift from mannual analogue process to a digital workflow system. 3. Reduced turn - around time. 4. Increased Customers Satisfaction and Feedback Redress Mechanism. | Over 80% of the State Registered CofO have been digitised and archived. | Plans are in place to ramp up the outstanding 31st December 2025.
|  |  | Issue Executive Order on FRILIA | The Executive Order provides a legal basis for the insitution of FRILIA practices in Lagos State | Investors, farmers and land owners | Ministry of Justice | Lands Bureau, Ministry of Housing, Ministry of Physical Planning and Urban Development, Office of the State Surveyor General | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 2024-01-10 | Ongoing 1. The is increased Inter-Agency Coordination, especially amongst Agric-Land Holdings Agency and the Main Ministry of Agriculture, Lands Bureau and the Ministry of Justice. 2. There is a noticeable pause on large-scale agricultural land allocation until FRILIA Compliant procedures are in place. | 1. Land Based MDAs are now jointly trained as recommended by the State FRILIA Policy. 2. There is a considerable increase in request for Due Diligence by Investors on availability of Agric-Land in Lagos State. | 1. Public Awareness and Sensitisation of Lagos State's Adoption of FRILIA. 2. Completion of the Mapping and the Categorisation Process State Owned Land to determine and validate the suitable Agriculture Land for future Allocation.
|  |  | Institute the Framework for Responsible and Inclusive Land Intensive Agriculture (FRILIA) | (i) Establish a Steering Committee on FRILIA (ii) Create an interministeral consultative platform for FRILIA challenges | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; Ministry of Physical Planning and Urban Development; Ministry of Justice, Ministry of Finance, Ministry of Commerce, Cooperatives, Trade and Investment, LIRS, Office of the Surveyor-General | LCCI, MAN, NASME, NACCIMA | N500,000,000 | 2024-01-01 | 31-12-24 | Done !. There is a visible improvement in Interministeral Coordination and drastic reduction in Silo workings. 2. Resource mobilisation and allocation are now done more efficiently, as efforts are no longer duplicated. 3. Another major impact is the achievement of Policy Coherence and Regulatory Alignment. All stakeholder MDAs now aligns with FRILIA objectives and also adaptive to developmental frameworks. | The State's Interministeral Consultative Platform for FRILIA is programmatically coordinated by the State Electronic Geographic Information System (eGIS), Ministry of Agric and Office of Surveyor General.. | 1. Sustained Public Awareness and Sensitisation of Lagos State's Adoption of FRILIA. (i.e., bi-annually)
|  |  | Develop FRILIA toolkit | Establish specific tools for implementing FRILIA in the State | Investors, farmers and land owners | Ministry of Agriculture | Land Bureau, Ministry of Housing; Ministry of Physical Planning and Urban Development; Ministry of Justice, Ministry of Finance, Ministry of Commerce, Cooperatives, Trade and Investment, LIRS, Office of the Surveyor-General | LCCI, MAN, NASME, NACCIMA | N600,000,000 | 2024-01-01 | 31-12-24 | Ongoing Increased efforts to deepen the mapping and categorisation of state-owned land that are suitable for Agricultural purposes. | 1. Internal Statekeholders in the Land Family (i.e. Lands Bureau, Ministry of Agric, Survey etc.) are beginning to deepen the clarity of their mandates as pronunced by the new FRILIA Policy. This has led to the reduction of irresponsible middle men and speculative actors. 2. Nothwithstanding, the ongoing efforts of the Government have also led to the identification of lands with disputes and overlapping titles, which takes time to resolve owing to legal interpretations. | 1. Sustained Capacity Development of Internal Stakeholders and Continuous Sensitisation of the Investing Public
2 | Develop an effective framework for Public Private Partnerships and Improved Investment Promotion Environment | Establish effective Public-Private Partnership (PPP) framework for the State | Create PPP disclosure portal of the pipeline projects | Create a PPP disclosure portal on her website and state official website. | Investors | Office of Public Private Partnership | Ministry of Commerce, Cooperatives, Trade and Investment; Ministry of Economic Planning and Budget; Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | N10,000,000 | 2024-01-01 | 31-03-24 | Completed 1. There is an improvement in Investor Confidence meassured by the increase in search and request for transactions in the State's Deals Pipeline by would-be investors. 2. The Office of Public Private Partnership has significantly improved upon its knowledge management and streamlined processes, thereby reducing time spet by government officialis to respond to public information requests. | 1. There is an enhanced transparency and public trust, underscored by the increase in public scrutiny, i.e. media reports, performance reports e.t.c. 2. The is also a noticeable increase in Investors Confidence and Market Development. This is hinged on the availability of the same record to all bidders, thereby promoting fair competition and potentially lowering bidding costs. | 1. The State Government shall pursue the strengthening of its governance and performance structures by establishing an early warning system to identify early any impediments to the implementation of successful bids.
|  |  | Organise periodic information sessions annually for investors | Engage with stakeholders at least twice in 2024 with a view to removing bureaucratic constraints in the business environment in Lagos State | Investors | Ministry of Commerce, Cooperatives, Trade and Investment | Office of Public Private Partnership; Ministry of Economic Planning and Budget; Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | N7,000,000.00 | 2024-01-01 | 31-12-24 | (Ongoing - Bi-Annually) !. The frequent engagement with stakeholders has significantly improved the State's Feedback loop, through real time market intelligence. 2. There is also a noticeable integration of the Small and Medium Enterprises (SMEs) with local suppliers, leading to inclusive growth, job creation, which aligns with Lagos Economic Inclusion Agenda. | !. The Stakehokeholders Session is now Institutionalised and christened "Lagos Annual Investment Summit", with the maiden edition held in July 2024. Challenges? There are no challenges in obtaining the Approval to ensure the sustainability of the Summit, owing to the values extractable to the State. | 1. Early preparation for and enlarging the Stakeholder participation for year 2 version of Investment Summit to take stock of the gains of year 1 and chart the way forward for year 3.
|  |  | Develop a PPP Fiscal Commitment and Contingent Liability (FCCL) Management Framework; and (ii) the PPP legal and institutional framework, including guidelines and manual; and (iii) the PPP disclosure framework; | Lagos Global to create a PPP disclosure portal on her website and state official website. | Investors | Office of Public Private Partnership | Ministry of Commerce, Cooperatives, Trade and Investment; Ministry of Economic Planning and Budget; Public Procurement Agency | LCCI, MAN, NASME, NACCIMA | N10,000,000 | 2024-01-01 | 31-03-24 | Ongoing 1. There is an improvement in Investor Confidence meassured by the increase in search and request for transactions in the State's Deals Pipeline by would-be investors. 2. The Office of Public Private Partnership has significantly improved upon its knowledge management and streamlined processes, thereby reducing time spet by government officialis to respond to public information requests. | 1. There is an enhanced transparency and public trust, underscored by the increase in public scrutiny, i.e. media reports, performance reports e.t.c. 2. The is also a noticeable increase in Investors Confidence and Market Development. This is hinged on the availability of the same record to all bidders, thereby promoting fair competition and potentially lowering bidding costs. Challenges.......... Closing the capacity gap of the operating personnel requires adequate funding and time offs. | Next Steps 1. Complete Drafting of Frameworks for the PPP Portal. 2. Develop Implementation Guidelines. 3. Obtain Executive Approvals and Conduct Stakeholder Sensitisations.
|  |  | Establish State Project Facilitation Fund with a minimum funding of 3% of the total pipeline estimated capital investment | Catalyze public private investments with facilitation fund | Investors | Office of Public Private Partnership | Ministry of Commerce, Cooperatives, Trade and Investment, Public Procurement Agency, Ministry of Finance, Ministry of Budget and Economic Planning | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 30-06-24 | Ongoing The immediade impacts include, but are not limited to the following: 1. The turnaround time for Pre-Project Delivery Processing (i.e., Pre-Feasibility Studies, ESIA e.t.c.. ) has improved significantly, thereby catalysing more private sector requests and involvement. 2. The Reform has brought to for the need to carry out capacity gap assessment with a view to deepen the State's efforts aligning its Policies, Institutional Framework to suit the growing demand of the investment clime. | 1. The request for the creation of the State's Project Facilitation Fund is already in progress. 2. An initial Stakeholders Engagement to sensitise highly capital intensive projects delivery MDAs on the importance of establishing the Fund has been carried out. Challenges 1. The major challenge is the accurate estimation of all the projects in the projects pipeline in view of the uncertainty of the macroeconomic variables. | Next actionable steps needed: 1. Lagos OPPP is in the process of Developing a Framework to design the funding and operations of the proposed Fund. 2. This shall be followed by the constitution of a PPP Project Preparation Fund Committee (PPPFC) to manage the Inter-Agency Coordination and Funding of Approved Investment Projects. 3. Finally, a Stakeholder Awareness Campaign of the new Fund shall be launched.
3 | Simplification of State and Local Business Tax Regimes | This reform is aimed at introducing a fairer and more equitable in Lagos State | At least 10% increase in the number of firms in the state that obtained export certificates from NEPC from the baseline year (2021). | Create incentives for MSMEs engaging in non-oil export | Micro, Small and Medium Entreprises (MSMEs) and investors | Ministry of Commerce, Cooperatives, Trade and Investment | Ministry of Finance, Office of Taxation and Revenue, Ministry of Economic Planning and Budget, Ministry of Transportation and LIRS | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 2024-08-30 | Ongoing 1. The State has formalised the adoption of Lagos Global, currently operating from the Ministry of Commerce, Cooperatives, Trades and Investments (MCCTI) as its Investment Promotion Agency, via an Executive Order issued by the Governor on 21st July 2024. | 1. There is an ongoing realignment of functions, development of operational policy and capacity development to ensure optimal performance and delivery of the mandates of the reformalised IPA. Challenges 1. Mandates realignment of units and departments fussing into the re-formalised IPA. may take a while. | Next Step 1. The State shall reestabilish and deepen its collaration with the Nigeria Investment Promotion Council with a view to clearing the backlog of MSMEs that have applied for the issuance of Export Certificate.
|  |  | Amend existing legislation to adopt presumptive turnover tax regime for small businesses | Strengthen progressive taxation in Lagos State | Micro, Small and Medium Entreprises (MSMEs) and investors | LIRS | Ministry of Finance, Office of Taxation and Revenue, Ministry of Economic Planning and Budget, Ministry of Commerce, Cooperatives, Trade and Investment | LCCI, MAN, NASME, NACCIMA | Not Applicable | 2024-01-01 | 2024-08-30 | Ongoing 1. The State has witnessed a significant improvement in Tax Compliance, reduction in evasion and higher revenues. 2. There is also a drastic reduction in administrative delays as businesses can now file their returns and pay from the convenience of their offices. | There is gradual reduction in the cases of extortions from not too literate tax-payers owing to the simplification of the tax administrative process. Limitations However, more work still needs to be done is the aspect of speaking the tax language in orther forms i.e., pidgin, yoruba to ensure inclusivity and to also support the efforts within tangible supports i.e., public latrines for clustres of markets and artisans workshop. | Next Steps 1. Seek and Obtain Approval for further sensitisation at the grassroot level. 2. Adopt the Carrot approach of providing basic amenities to endear more tax payers to voluntary compliance.
4 | Quick determination of commercial disputes | This reform area will improve the State Judiciary and strengthen access to an efficient commercial justice system | Establish Additional Small Claims Courts | Set-Up two (2) additional Small Claims Courts to enable the Lagos State Judiciary address the plethora of cases filed daily | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Judiciary | Ministry of Justice | NBA, LCCI, MAN, NASME, NACCIMA | N200,000,000.00 | 2024-01-01 | 30-06-24 | Completed 1. To improve quick dispensation of small claims cases, the Lagos State Government established six (6) additional Small Claims Courts (SCC) in 2024. 2. The major hurdle to manage is the integration and expansion of the Sheriff Department to ensure prompt execution decided cases. | The small businesses in Agbowa at Ikorodu and Iba in the Ojo Local Government Areas of the State now have easy access to justice. Limitations Safe for paucity of funds and personnel, more SCC would have been created in other areas that are currently underserved with Small Claims Legal System. | Next Steps 1. Seek and obtain the Approval for the creation of a Specialised and well resourced Enforcement Unit within the Sheriff Departments, that will focus solely on the enforcement of SCC judgements effectively and efficiently. 2. Seek and obtain approval for the establishment of a secure End-to-End E-Filing Platform for filing claims, paying fees, serving documents etc.
|  |  | Improve Adherence to the 60-Day Timeline for the Disposition of Cases in the Small Claims Courts | Ensure that (25 - 50)% of Cases withing the Courts are disposed within 60days | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Judiciary | Ministry of Justice | NASME | Not Applicable | 2024-01-01 | 30-06-24 | Ongoing The State SCC has recorded improvement in the adherence of 60 days timeline for disposition of properly and completely filed cases, even below 60 days. Limitation The apparent challenge remains in prompt execution of decided cases. | 1. Over 50% of cases are disposed within 60 days, subject to parties meeting all terms and conditions. 2. Another challenge is in the judical process that requires certain time lines for filings, depositions, adjudications and responses. 3. It is important to state that the Execution of Judgement is governed by the Sheriffs and Civil Processes Act, as such Judgements of any Court is initiated by the Judgement Creditorand not the Court. 4. Therefore, the performance of the Judiciary on speedy disposition of Judgements can only be assessed sequel to the initiation of the Execution Process by the Judgement Creditor. | Next Step 1. The State Judiciary shall seek and obtain approval to Simplify and Optimise its Post-Judgement Enforcement Process (i.e., warrants, attachments, garnishment etc.,) specifically for the SCC.
|  |  | Improve Adherence to the 30-Day Timeline for the Execution of Judgement. | Ensure that (25 - 50)% of Judgement are Executed within 30days | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Judiciary | Ministry of Justice | NASME | Not Applicable | 2024-01-01 | 30-06-24 | Ongoing Same as above | 1. The Sheriff Department under the Judiciary shall continue to deepen its efforts to achieve the projectd 30 days timeline for the execution of judgements. 2. Some lacunas within the existing laws that allows for appeals and other form of objections make the attainment of the 30 days timeline herculean. 3. As earlier earlier, the Execution of Judgement is NOT within the purview of the Judiciary, but within the purview of the Law Enforcement Governance Structures that manage the Sheriff Department. | Next Step Same as above
|  |  | Track the Performance of the Small Claims Courts | Develop and Publish the Small Claims Courts Performance Reports on the State Judiciary Website on a Monthly basis. | Small Businesses - Small and Medium Entreprises (SMEs), Business Owners and investors | Lagos State Judiciary | Ministry of Justice | NASME | Not Applicable | 2024-01-01 | 30-06-24 | Ongoing This is an ongoing reform. Currently, the Lagos State Small Claims Courts Performance Reports are constantly and consistently published on a monthly basis on the State website. | Currently, the Performance of SCC is done on a monthly basis with Performance Reports published on a monthly basis ex-post-facto. | Next Step The State is considering the Creation of a Transparent Performance Tracking Field within its eixisting structure where Claimers can be provided with tokens to track the enforcement of their cases real-time.
- ⁠Action step - Track the performance of the small claims courts.
- ⁠Key Target - Develop and publish the Small Claims Court Performance Report on the state judiciary website on a monthly basis.